# X4O Project Milestones - Sheet Summary & Reports Configuration

Project: X4O Website Redevelopment

Company: X4O (Pty) Limited

Document Type: Smartsheet Data Configuration Guide

Date: February 12, 2026

Prepared By: Keenan Husselmann

Version: 1.0

---

## Table of Contents

1. [Introduction](#introduction)

2. [Technical Terms Glossary](#technical-terms-glossary)

3. [Part 1: Sheet Summary Fields](#part-1-sheet-summary-fields)

4. [Part 2: Create Reports](#part-2-create-reports)

5. [Verification & Testing](#verification--testing)

6. [Troubleshooting](#troubleshooting)

---

## Introduction

This guide walks you through setting up Sheet Summary Fields and Reports for the X4O Project Milestones sheet. These data sources will power your dashboard widgets.

### What You'll Configure

Sheet Summary Fields (12 fields):

Aggregate metrics that calculate automatically

Foundation for dashboard KPI widgets

Real-time updates as sheet changes

Reports (6 reports):

Filtered views of milestone data

Data source for dashboard tables and charts

Custom views for different audiences

### Prerequisites

✅ X4O Project Milestones sheet imported and configured

✅ Column types set correctly (Dropdown, Date, Contact List)

✅ Conditional formatting applied

✅ 15-20 minutes of time

---

## Technical Terms Glossary

For Non-Technical Readers: Simple explanations of Smartsheet concepts.

| Term | Simple Explanation |
| --- | --- |
| **Sheet Summary** | A summary panel at the top of a sheet showing key metrics. Like a scoreboard showing totals and averages. |
| **Summary Field** | A single calculated metric in Sheet Summary. Like one gauge on a car dashboard (speed, fuel, etc.). |
| **Formula** | Automatic calculation that updates when data changes. Like a calculator that recalculates automatically. |
| **COUNT** | Counts how many items exist. Like counting people at a meeting. |
| **COUNTIF** | Counts items matching a condition. Like counting only people wearing blue shirts. |
| **SUM** | Adds numbers together. Basic addition. |
| **AVG (Average)** | Calculates the mean of numbers. Sum divided by count. |
| **Report** | A filtered view of sheet data. Like a custom view showing only relevant information. |
| **Filter** | Shows only rows meeting specific criteria. Like a search that hides non-matching items. |
| **Group By** | Organizes data into categories. Like sorting files into folders. |
| **Sort** | Arranges data in order (A-Z, newest first, etc.). Like alphabetizing or chronological order. |
| **Aggregation** | Combining data to show summaries. Like monthly sales totals instead of individual transactions. |

---

## Part 1: Sheet Summary Fields

### What is Sheet Summary?

Sheet Summary is a panel at the top of your sheet that displays key metrics and calculations. Think of it as your sheet's dashboard - always visible, always up-to-date.

### Access Sheet Summary

1. Open Sheet

- Navigate to: `X4O Project Milestones` sheet

2. Open Sheet Summary Panel

- Method 1: Click "Sheet Summary" icon in right panel

- Method 2: Click the summary icon in toolbar (looks like a list with checkboxes)

- Method 3: Right-click sheet tab → "Sheet Summary"

3. Panel Opens

- Right side panel displays

- Shows "Add field" button

- Empty if first time opening

---

### Configure Sheet Summary Fields

We'll create 12 summary fields to track project metrics.

---

#### Field 1: Total Milestones

Purpose: Count total number of milestones in project

Steps:

1. Click "+ Add Field" in Sheet Summary panel

2. Field Name: `Total Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNT([Milestone Name]:[Milestone Name])

```

5. Expected Value: 38

6. Click "OK"

What it does: Counts all rows with milestone names (excludes header row)

---

#### Field 2: Completed Milestones

Purpose: Count milestones with "Complete" status

Steps:

1. Click "+ Add Field"

2. Field Name: `Completed Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Status:Status, "Complete")

```

5. Expected Value: 28

6. Click "OK"

What it does: Counts rows where Status column = "Complete"

---

#### Field 3: In Progress Milestones

Purpose: Count milestones currently being worked on

Steps:

1. Click "+ Add Field"

2. Field Name: `In Progress Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Status:Status, "In Progress")

```

5. Expected Value: 0

6. Click "OK"

What it does: Counts rows where Status = "In Progress"

---

#### Field 4: Not Started Milestones

Purpose: Count milestones not yet begun

Steps:

1. Click "+ Add Field"

2. Field Name: `Not Started Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Status:Status, "Not Started")

```

5. Expected Value: 10

6. Click "OK"

What it does: Counts rows where Status = "Not Started"

---

#### Field 5: Overall % Complete

Purpose: Calculate average completion percentage across all milestones

Steps:

1. Click "+ Add Field"

2. Field Name: `Overall % Complete`

3. Field Type: Formula

4. Formula:

```

=AVG([% Complete]:[% Complete])

```

5. Format: Percentage (1 decimal place)

6. Expected Value: 73.7%

7. Click "OK"

What it does: Averages the % Complete column (0, 50, 100 → average)

---

#### Field 6: Critical Milestones

Purpose: Count milestones with Critical priority

Steps:

1. Click "+ Add Field"

2. Field Name: `Critical Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Priority:Priority, "Critical")

```

5. Expected Value: 7

6. Click "OK"

What it does: Counts rows where Priority = "Critical"

---

#### Field 7: High Priority Milestones

Purpose: Count high priority items

Steps:

1. Click "+ Add Field"

2. Field Name: `High Priority Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Priority:Priority, "High")

```

5. Expected Value: 20

6. Click "OK"

---

#### Field 8: Phase 7 (Maintenance) Count

Purpose: Count milestones in Phase 7

Steps:

1. Click "+ Add Field"

2. Field Name: `Phase 7 Milestones`

3. Field Type: Formula

4. Formula:

```

=COUNTIF(Phase:Phase, "Phase 7: Maintenance")

```

5. Expected Value: 10

6. Click "OK"

What it does: Counts ongoing maintenance tasks

---

#### Field 9: Completed Phases

Purpose: Count how many phases are 100% complete

Steps:

1. Click "+ Add Field"

2. Field Name: `Completed Phases`

3. Field Type: Formula

4. Formula:

```

=6

```

*(Static value - Phases 1-6 complete, Phase 7 in progress)*

5. Expected Value: 6

6. Click "OK"

Note: This is a manual field. Update to 7 when Phase 7 completes.

---

#### Field 10: Project Start Date

Purpose: First milestone start date (project kickoff)

Steps:

1. Click "+ Add Field"

2. Field Name: `Project Start Date`

3. Field Type: Formula

4. Formula:

```

=MIN([Start Date]:[Start Date])

```

5. Expected Value: 2026-02-07

6. Click "OK"

What it does: Finds earliest start date in entire sheet

---

#### Field 11: Latest Milestone Date

Purpose: Last milestone end date (project completion estimate)

Steps:

1. Click "+ Add Field"

2. Field Name: `Latest Milestone Date`

3. Field Type: Formula

4. Formula:

```

=MAX([End Date]:[End Date])

```

5. Expected Value: 2027-02-15 (Annual Domain Renewal)

6. Click "OK"

What it does: Finds latest end date in sheet

---

#### Field 12: Days Since Project Start

Purpose: How many days since project kickoff

Steps:

1. Click "+ Add Field"

2. Field Name: `Days Since Start`

3. Field Type: Formula

4. Formula:

```

=TODAY() - MIN([Start Date]:[Start Date])

```

5. Format: Number (no decimals)

6. Expected Value: ~5 days (as of Feb 12, 2026)

7. Click "OK"

What it does: Calculates days between today and first start date

---

### Sheet Summary Panel Complete

You should now see:

Sheet Summary
─────────────────────────────────────
Total Milestones:              38
Completed Milestones:          28
In Progress Milestones:        0
Not Started Milestones:        10
Overall % Complete:            73.7%
Critical Milestones:           7
High Priority Milestones:      20
Phase 7 Milestones:            10
Completed Phases:              6
Project Start Date:            2026-02-07
Latest Milestone Date:         2027-02-15
Days Since Start:              5

These fields will auto-update as you modify the sheet (change statuses, add milestones, etc.).

---

## Part 2: Create Reports

### What are Reports?

Reports are filtered, sorted views of your sheet data. They pull data from the source sheet but display only what you specify. Perfect for dashboard widgets and stakeholder views.

### Access Reports

1. Navigate to Home

- Click "Home" in left sidebar

2. Create New Report

- Click "Create" button (top-left)

- Select "Report" from menu

---

### Report 1: Upcoming Milestones

Purpose: Show next 10 milestones starting soon (Not Started status)

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - Upcoming Milestones`

2. Add Source Sheet

- Click "+ Add Source Sheet"

- Select: `X4O Project Milestones`

- Check "Include all columns"

- Click "OK"

3. Configure Filters

- Click "Add Filter" (funnel icon)

Filter 1:

- Column: Status

- Condition: is

- Value: Not Started

Filter 2:

- Column: Start Date

- Condition: is within

- Value: next 90 days

4. Configure Columns

- Show only: Milestone Name, Phase, Start Date, Priority, Owner, Deliverables

- Hide other columns (click column header → Hide Column)

5. Sort Data

- Click "Sort" icon

- Primary Sort: Start Date (Ascending - earliest first)

- Secondary Sort: Priority (Critical → Low)

6. Group Data (Optional)

- Click "Group" icon

- Group By: Phase

- Shows milestones organized by phase

7. Save Report

- Click "Save" (top-right)

Expected Result: 10 upcoming Phase 7 milestones displayed

---

### Report 2: Critical Milestones

Purpose: All milestones with Critical priority (regardless of status)

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - Critical Milestones`

2. Add Source Sheet

- Source: `X4O Project Milestones`

- Include all columns

3. Configure Filter

- Column: Priority

- Condition: is

- Value: Critical

4. Configure Columns

- Show: Milestone Name, Status, Start Date, End Date, % Complete, Owner

5. Sort Data

- Primary Sort: Status (Complete last, Not Started first)

- Secondary Sort: Start Date (Ascending)

6. Highlight Rows (Conditional Formatting)

- Format → Conditional Formatting

- Rule: If Status is "Not Started"

- Format: Red background (#ffc7ce), Red text (#9c0006)

- Apply to: Entire row

7. Save Report

Expected Result: 7 critical milestones (3 deployment, 1 testing, 3 Phase 7)

---

### Report 3: Phase 7 - Maintenance Items

Purpose: All Phase 7 ongoing/future tasks

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - Phase 7 Maintenance`

2. Add Source Sheet

- Source: `X4O Project Milestones`

3. Configure Filter

- Column: Phase

- Condition: is

- Value: Phase 7: Maintenance

4. Configure Columns

- Show: Milestone Name, Priority, Start Date, End Date, Status, Category, Dependencies

5. Group Data

- Group By: Category

- Shows Enhancement, Operations, Compliance groups

6. Sort Within Groups

- Sort: Priority (Critical → Low)

7. Save Report

Expected Result: 10 Phase 7 tasks grouped by category

---

### Report 4: Completed Milestones by Phase

Purpose: Historical view of what's been accomplished

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - Completed Milestones`

2. Add Source Sheet

- Source: `X4O Project Milestones`

3. Configure Filter

- Column: Status

- Condition: is

- Value: Complete

4. Configure Columns

- Show: Milestone Name, Phase, End Date, Deliverables, Owner

5. Group Data

- Group By: Phase

- Shows completed items per phase

6. Sort

- Within Groups: End Date (Descending - newest first)

7. Summary Row (Optional)

- Click group header → "Summarize"

- Add: Count of Milestones

- Shows total completed per phase

8. Save Report

Expected Result: 28 completed milestones grouped by Phase 1-6

---

### Report 5: High Priority Pending

Purpose: High priority items not yet started (for planning)

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - High Priority Pending`

2. Add Source Sheet

- Source: `X4O Project Milestones`

3. Configure Filters

Filter 1:

- Column: Priority

- Condition: is one of

- Values: Critical, High (select both)

Filter 2:

- Column: Status

- Condition: is

- Value: Not Started

4. Configure Columns

- Show: Milestone Name, Priority, Category, Start Date, Dependencies, Notes

5. Sort

- Primary: Priority (Critical first)

- Secondary: Start Date (Ascending)

6. Save Report

Expected Result: ~8-10 high priority pending items

---

### Report 6: Timeline View (All Active)

Purpose: Gantt-friendly report for dashboard timeline widget

Steps:

1. Create Report

- Create → Report

- Report Name: `X4O - Timeline View`

2. Add Source Sheet

- Source: `X4O Project Milestones`

3. Configure Filters

- Filter: Status is one of "Complete", "In Progress", "Not Started"

- *(Include all - this filter just ensures data integrity)*

4. Configure Columns

- Required: Milestone Name, Start Date, End Date, Status, Phase

- Optional: % Complete, Priority

5. Sort

- Primary: Phase (Phase 1 → 7)

- Secondary: Start Date (Ascending)

6. Save Report

Expected Result: All 38 milestones in chronological order by phase

Note: This report is specifically formatted for Gantt chart widgets in dashboards.

---

## Verification & Testing

### Test Sheet Summary Fields

Steps:

1. Open Sheet Summary Panel

- Verify all 12 fields display correctly

2. Test Formula Updates

- Action: Change one milestone Status from "Not Started" to "Complete"

- Expected:

- Completed Milestones: 28 → 29

- Not Started Milestones: 10 → 9

- Overall % Complete: 73.7% → 76.3%

3. Undo Test Change

- Ctrl+Z to revert status change

- Verify metrics return to original values

4. Check Static Fields

- Verify Completed Phases = 6

- Verify Project Start Date = 2026-02-07

✅ All fields should update automatically when sheet data changes

---

### Test Reports

For each report, verify:

| Report | Expected Row Count | Key Filter Working |
| --- | --- | --- |
| **Upcoming Milestones** | 10 | Only "Not Started" shown |
| **Critical Milestones** | 7 | Only "Critical" priority |
| **Phase 7 Maintenance** | 10 | Only Phase 7 items |
| **Completed Milestones** | 28 | Only "Complete" status |
| **High Priority Pending** | 8-10 | Only High/Critical + Not Started |
| **Timeline View** | 38 | All milestones included |

Test Report Refresh:

1. Open any report

2. Make change in source sheet

- Example: Change a milestone status

3. Refresh report

- Click refresh icon or F5

4. Verify change reflected

- Row should move/disappear based on filter

✅ Reports should update when source sheet changes

---

### Create Report Folder (Organization)

Steps:

1. Navigate to Home

2. Right-click in left sidebar

3. Select "New Folder"

4. Folder Name: `X4O Project Reports`

5. Drag all 6 reports into folder

Result: Reports organized in dedicated folder for easy access

---

## Troubleshooting

### Issue: Sheet Summary Field Shows #UNPARSEABLE

Symptoms:

Formula shows error instead of value

Field displays #UNPARSEABLE or #INVALID REF

Diagnosis:

Column name mismatch

Incorrect formula syntax

Column type incompatible

Resolution:

1. Edit Field

- Click field → Edit

2. Check Column Names

- Verify exact spelling: `[Milestone Name]:[Milestone Name]`

- Column names are case-sensitive

- Include square brackets for multi-word names

3. Verify Formula Syntax

Correct:

```

=COUNTIF(Status:Status, "Complete")

```

Incorrect:

```

=COUNTIF([Status], "Complete")  ← Missing column range

=COUNTIF(Status, "Complete")    ← Missing second reference

```

4. Check Quotes

- Use straight quotes: `"Complete"`

- Not curly quotes: `"Complete"` ← Wrong

5. Save and Verify

---

### Issue: Report Shows No Data

Symptoms:

Report displays "No data to display"

Expected rows missing

Diagnosis:

Filters too restrictive

Source sheet disconnected

Column hidden in source

Resolution:

1. Check Filters

- Click filter icon

- Review all active filters

- Temporarily disable filters (toggle off)

- If data appears, filters are too restrictive

2. Adjust Filter Values

- Verify dropdown values match exactly

- Example: "Complete" not "Completed"

- Case-sensitive matching

3. Check Source Sheet

- Click "Source Sheets" tab in report

- Verify `X4O Project Milestones` is listed

- If missing, re-add source sheet

4. Verify Columns Exist

- Open source sheet

- Confirm filtered columns exist

- Check column names match filter

---

### Issue: Report Data Not Updating

Symptoms:

Report shows old data after sheet changes

Manual refresh doesn't update

Diagnosis:

Browser cache

Report not linked to source

Permission issue

Resolution:

1. Hard Refresh

- Ctrl+Shift+R (Windows) or Cmd+Shift+R (Mac)

- Clears browser cache

2. Check Report-Sheet Link

- Open report

- Click "Source Sheets"

- Verify green checkmark next to sheet name

- If red X, re-add source sheet

3. Verify Permissions

- Ensure you have "Viewer" or higher access

- Owner/Admin can always see updates

4. Recreate Report (Last Resort)

- If issue persists, delete report

- Create new report with same settings

- Link to source sheet

---

### Issue: Formula Counting Wrong

Symptoms:

COUNTIF returns unexpected number

COUNT shows more/fewer than expected

Diagnosis:

Hidden rows

Blank cells counted

Filter applied to source sheet

Resolution:

1. Check Hidden Rows

- Source sheet → Unhide All Rows

- Menu: View → Show All

2. Verify Column Range

- Formula should reference entire column:

```

=COUNT([Milestone Name]:[Milestone Name])

```

- Not partial range:

```

=COUNT([Milestone Name]1:[Milestone Name]38)  ← Excludes new rows

```

3. Check for Blank Cells

- COUNT counts non-blank cells

- COUNTIF counts cells matching criteria

- If blanks exist, they're excluded

4. Remove Sheet Filters

- Source sheet → Clear all column filters

- Formulas count visible + hidden rows (unlike manual counts)

---

## Summary

### What You've Created

✅ Sheet Summary Fields (12 fields)

Total Milestones: 38

Completed Milestones: 28

In Progress: 0

Not Started: 10

Overall % Complete: 73.7%

Critical Milestones: 7

High Priority: 20

Phase 7 Count: 10

Completed Phases: 6

Project Start: 2026-02-07

Latest Milestone: 2027-02-15

Days Since Start: ~5

✅ Reports (6 reports)

1. Upcoming Milestones (10 rows)

2. Critical Milestones (7 rows)

3. Phase 7 Maintenance (10 rows)

4. Completed Milestones (28 rows)

5. High Priority Pending (8-10 rows)

6. Timeline View (38 rows)

### Next Steps

You're now ready to build the dashboard!

The dashboard will use:

Metric widgets → Pull from Sheet Summary fields

Chart widgets → Pull from source sheet or reports

Table widgets → Display reports

Gantt widget → Use Timeline View report

Proceed to:

`MILESTONES_DASHBOARD_SETUP.md` (Part 3: Create Dashboard)

---

## Quick Reference

### Sheet Summary Formula Templates

| Metric | Formula | Purpose |
| --- | --- | --- |
| **Count All** | `=COUNT([Column]:[Column])` | Total rows |
| **Count Specific** | `=COUNTIF(Column:Column, "Value")` | Rows matching value |
| **Average** | `=AVG([Column]:[Column])` | Mean of numbers |
| **Sum** | `=SUM([Column]:[Column])` | Add all numbers |
| **Earliest Date** | `=MIN([Date]:[Date])` | First date |
| **Latest Date** | `=MAX([Date]:[Date])` | Last date |
| **Days Between** | `=TODAY() - [Date]` | Days since date |
| **Percentage** | `=(Part / Total) * 100` | Calculate % |

### Report Best Practices

✅ Filter Wisely

Start broad, narrow as needed

Test filters with sample data

Document filter logic in report name

✅ Column Selection

Show only relevant columns

Hide internal/technical columns

Order columns logically (important → detail)

✅ Grouping

Group by phase, status, or category

Add summary rows to groups

Collapse groups for overview

✅ Sorting

Primary sort = most important category

Secondary sort = chronological or priority

Consistent sorting across similar reports

✅ Naming Convention

Prefix with project: `X4O - Report Name`

Descriptive: Say what it shows

Consistent: All reports follow same pattern

---

## Document Information

Document Version: 1.0

Last Updated: February 12, 2026

Prepared By: Keenan Husselmann

Status: ✅ Complete

Related Documents:

`X4O_Project_Milestones.csv` (source data)

`MILESTONES_DASHBOARD_SETUP.md` (dashboard instructions)

Next Document: Ready to build dashboard (Part 3)

---

END OF DOCUMENT